## Metrics
|  | Active contract |  |  | Value | Count |  | SPA Value | Count | Value incl SPA |  |  |  | Current | 2010-4 |  |  |  | #N/A |  | #N/A |  | #N/A | [5 empty] | Threshold |  | -1 | -1 |  | 30% |  |  |  |  | -10000 | 30% |  | 8% |  | 7000 | 7000 |  |  | 2 | 10000
|  | BPGDM US |  |  | 2755222.96 | 21 |  | 83622 | 5 | 2838844.96 |  |  |  | Format: 2008-5 |  |  |  |  | #N/A |  | 0 |  | #N/A | [7 empty] | n over run > 20K |  |  | 40% |  |  |  |  | n over run > 20K | 40% |  | n % var > 10% | [5 empty] | n < -10K | n > 50K
|  | BPGDM UK |  |  | 186505 | 1 |  | 0 | 0 | 186505 | [8 empty] | 0 |  | #N/A |  | 0 | [7 empty] | n over run > 10K | [7 empty] | n over run > 10K |  |  | n % var > 8% | [5 empty] | n > 10K | n > 30K
|  | Total GDM UK |  |  | 0 | 0 |  | 0 | 0 | 0 | [8 empty] | GROWTH STATISTICS
|  | Maersk GDM UK |  |  | 0 | 0 |  | 0 | 0 | 0 | [20 empty] | MM
|  | Total Other UK |  |  | 0 | 0 |  | 0 | 0 | 0
|  | US |  |  | 2755222.96 | 21 |  | 83622 | 5 | 2838844.96 | [40 empty] | a=Elance
|  | UK |  |  | 186505 | 1 |  | 0 | 0 | 186505 | [13 empty] | CONTRACTUAL STATUS | [6 empty] | ACT FINANCIAL HEALTH | [7 empty] | EAC PREDICTIVE HEALTH |  |  |  |  | BILLING | [11 empty] | P11ME |  |  | P12ME
|  | Total | hide | hide | 2941727.96 | 22 | hide | 83622 | 5 | 3025349.96 | [8 empty] | Changes since prior period |  |  |  |  | SPA |  |  |  | POP | POP |  | Over run | Over run | Over run | GM% | Unbillable | Unbillable | Loss |  | Over run | GM% | Loss | EAC vs Act |  | Aging |  | Unbilled | [7 empty] | SPA |  | Financial | [6 empty] | EAC | Act
Project # | EL/PO | Project Name | Rate Card | Start POP | End POP | Project Type | Period | Project Manager | Project Controller | RO/COValue | BCA Value | SPA Value | Total Value | Contract | US/UK | Complete | WBS closed | e1 | New | CO | CO $ | POP ext | Completed | Expire | Value | In prog | $ cover | e2 | 2009-12-31 |  | P12ME | Incl SPA | very close | P12ME | As of P12ME | FY2009 | P12ME | e3 | P4 EAC | P4 EAC | P4 EAC | GM% | e4 | >90 days | >181 days | Last billed | Last Per | P3 10 | Imputed $ | $K | Elance | Notes |  | Status | Expire Date | Act Rev | Act Cost | Over/Under | Act Rev | Act Cost | Over/Under | Unbilled | Overrun | Overrun
Project # |  | Project Name | Rate Card | Start POP | End POP | Project Type | Period | Project Manager | Project Controller | [5 empty] | US/UK | Complete |  | e1 | [5 empty] | SPA exp | Value | In prog | $ cover | BCA | POP | 0 | Act Over | Incl SPA |  | M |  |  | Act Loss | e3 | EAC over | EAC GM% | EAC Loss | EAC vs Act GM var | e4 | >90 days | >181 days | Last billed | Last Per | Old Bill | Unbilled | Unbilled $K |  | Notes
16520 |  | Project 1 | BP UP_UK_TM P10 FY10 | 2008-12-08 | 2009-03-21 | TM | P2 ME | xxxxx | xxxxx | 208458 | 0 | 0 | 208458 | Project | US | COMPLETE | a | [16 empty] | 53.87% | [11 empty] | 2009-03-09 | P2 10 |  |  |  | a |  |  |  |  | 148777.06 | 68627.97 | 59680.94 | 148777.06 | 68627.97 | 59680.94 | -198.56 | 59680.94 | 59680.94
17130 |  | Project 2 | 16520 | 2008-01-31 | 2009-08-10 | TM | P3 ME | xxxxx | xxxxx | 372329 | 0 | 0 | 372329 | Data Management | US | COMPLETE | a | [16 empty] | 31.92% | [5 empty] | 53.87% |  | n |  |  |  | 2009-03-09 | P2 10 |  | n | 23.491 |  | Received invoice from AR |  |  |  | 353671.22 | 240794.21 | 18657.78 | 353671.22 | 240794.21 | 18657.78 | -23490.96 | 61261.26 | 93657.09
17517 |  | Project 3 | 17130 | 2008-05-12 | 2009-03-15 | TM | P3 ME | xxxxx | xxxxx | 55879 | 0 | 0 | 55879 | Project | US | COMPLETE | a | [16 empty] | 49.48% | [5 empty] | 31.07% |  | n |  |  |  | 2009-03-18 | P2 10 |  |  |  | a |  |  |  |  | 50972.7 | 25752.32 | 4906.3 | 50972.7 | 25752.32 | 4906.3 | -267.04 | 4906.3 | 4906.3
17526 |  | Project 4 | 17517 | 2008-08-01 | 2009-01-31 | TM | P3 ME | xxxxx | xxxxx | 134965 | 0 | 0 | 134965 | Project | US | COMPLETE | a | [16 empty] | 51.23% | [5 empty] | 49.48% | [5 empty] | 2008-10-08 | P10 09 | a |  |  | a |  |  |  |  | 121353.25 | 59189.4 | 13611.75 | 121353.25 | 59189.4 | 13611.75 | -0.15 | 13611.75 | 13611.75
17612 |  | Project 5 | 17526 | 2008-08-08 | 2008-12-31 | TM | P3 ME | xxxxx | xxxxx | 147042 | 0 | 0 | 147042 | Project | US | CLOSED | a | [13 empty] | n | n |  | 55.18% | [5 empty] | 51.23% | [5 empty] | 2009-01-23 | P13 09 | a |  |  | a |  | Over run = -0.01K. |  |  | 147048.96 | 65906.65 | -6.96 | 147048.96 | 65906.65 | -6.96 | -523.85 | -6.96 | -6.96
17970 | 337896, 353303 | Project 6 | 17612 | 2008-09-01 | 2009-10-19 | TM-CHARGE-CODE | P3 ME | xxxxx | xxxxx | 677662.71 | 0 | 0 | 677662.71 | Data Management | US | COMPLETE | a | [13 empty] | n | n |  | 40.55% |  |  |  |  | n | 55.18% |  | n | [6 empty] | n | 225.515 |  | On SPA | Over run = 50.43K. |  |  | 681896.17 | 405401.82 | -4233.46 | 681896.17 | 405401.82 | -4233.46 | -225515 | -102499.75 | 50427.48
17972 |  | Project 7 | 17970 P13 TO DEC 31 | 2009-01-01 | 2008-12-31 | TM | P3 ME | xxxxx | xxxxx | 0 | 37178 | 0 | 37178 | Project | US | CLOSED | a | [16 empty] | 57.3% |  |  |  |  | n | 41.32% |  | n | [8 empty] | a | Project does not appear to have taken place | Over run = 26.9K. SPA = K |  |  | 10278.78 | 4389.51 | 26899.22 | 10278.78 | 4389.51 | 26899.22 | 0 | -10278.78 | 26899.22
18008 |  | Project 8 | 17972 | 2008-10-20 | 2009-04-03 | TM | P3 ME | xxxxx | xxxxx | 105457 | 0 | 0 | 105457 | Project | US | COMPLETE | a | [16 empty] | 48.55% | [5 empty] | 57.3% |  | n | [6 empty] | n | 103.0034 | a | See copy of invoices for P2, need to find in SAP - has Canadian Labor withholding | Over run = -6.1K. SPA = K |  |  | 105435.28 | 54245.47 | 21.72 | 105435.28 | 54245.47 | 21.72 | -103003.44 | -7609.41 | -6096.28
18171 | 337864 | Project 9 | 18008 P2FY10 MAR 1 | 2008-11-24 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 454355 | 0 | 0 | 454355 | Data Management | US | OPEN |  |  |  | a | 297568 | a | [5 empty] | n | [5 empty] | 55.43% | [5 empty] | 52.02% | [8 empty] | n | 94.5745 |  | Been on SPA | Over run = 305.1K. SPA = K |  |  | 404690.79 | 180350.54 | 49664.21 | 438839.46 | 195683.46 | 15515.54 | -94574.49 | 26638.35 | 305101.73
18172 | 337887 | Project 10 | 18171 | 2009-01-02 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 383349 | 0 | 0 | 383349 | Data Management | US | OPEN |  |  |  | a | 256207 | a | [5 empty] | n | [5 empty] | 52.89% | [5 empty] | 54.19% | [8 empty] | n | 125.8624 |  | Been on SPA | Over run = 247.24K. SPA = K |  |  | 332430.12 | 156610.33 | 50918.88 | 352242.85 | 166204.17 | 31106.15 | -125862.4 | 5743.7 | 247243.22
18333 | 319601 | Project 11 | 18172 | 2009-01-02 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 166993 | 0 | 0 | 166993 | Data Management | US | OPEN | [11 empty] | n |  |  | n | n |  | 49.31% | [5 empty] | 44.46% | [8 empty] | n | 41.1991 |  | Received invoice from AR |  |  |  | 137072.01 | 69487.47 | 29920.99 | 170588.12 | 85483.71 | -3595.12 | -41199.13 | 3340.98 | 111816.78
18348 | 319535 | Project 12 | 18333 | 2009-01-05 | 2009-11-30 | TM | P3 ME | xxxxx | xxxxx | 67018 | 0 | 0 | 67018 | Data Management | US | COMPLETE | a |  |  |  |  | a | [11 empty] | 62.11% | [5 empty] | 45.45% |  | n |  |  |  | 2009-03-19 | P2 10 |  | n | 13.4184 |  | Received invoice from AR |  |  |  | 56994.2 | 21595.42 | 10023.8 | 56994.2 | 21595.42 | 10023.8 | -13418.44 | 4988.37 | 28920.06
18942 |  | Project 13 | 18348 | 2008-12-01 | 2009-05-20 | TM-CHARGE-CODE | P3 ME | xxxxx | xxxxx | 0 | 15523 | 0 | 15523 | Data Management | US | COMPLETE | a |  |  |  |  | a | [11 empty] | 45.4% |  |  |  |  | n | 61.86% |  | n | [9 empty] | new |  |  |  | 3500.02 | 1910.89 | 12022.98 | 3500.02 | 1910.89 | 12022.98 | 0 | -15522.57 | 13577.92
19155 | 347474 | Project 14 | 18942 | 2009-03-30 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 69852.54 | 0 | 0 | 69852.54 | Data Management | US | OPEN |  |  | a | [8 empty] | n | [5 empty] | 46.92% | [5 empty] | 55.59% |  | n | [13 empty] | 39867.89 | 21162.19 | 29984.65 | 41924.34 | 22337.25 | 27928.2 | #N/A | 69852.54
19289 | 353872 | Project 15 | 19155 | 2009-04-27 | 2009-08-17 | TM | P3 ME | xxxxx | xxxxx | 14198 | 0 | 0 | 14198 | Data Management | US | COMPLETE | a |  | #N/A | #N/A | #N/A | #N/A | #N/A | [10 empty] | 46.54% | [21 empty] | 4809.67 | 2571.1 | 9388.33 | 4809.67 | 2571.1 | 9388.33 | #N/A
19290 |  | Project 16 | 17648 | 2008-09-01 | 2009-06-29 | TM | P3 ME | xxxxx | xxxxx | 0 | 0 | 0 | 0 | Data Management | US | CLOSED | a |  | #N/A | #N/A | #N/A | #N/A | #N/A | [16 empty] | 49.9% | [15 empty] | 0 | 16.44 | 0 | 0 | 16.44 | 0 | #N/A
19328 | 350837 | Project 17 | 17649 | 2008-09-04 | 2009-11-30 | TM | P3 ME | xxxxx | xxxxx | 68037.52 | 0 | 0 | 68037.52 | Data Management | US | COMPLETE | a |  | #N/A | #N/A | #N/A | #N/A | #N/A | [10 empty] | 49.29% | [5 empty] | 62.28% |  | n | [11 empty] | Negated | 2009-10-31 | 68030.27 | 34497.74 | 7.25 | 68030.27 | 34497.74 | 7.25 | #N/A
19365 | NON-ELANCE | Project 18 | 18367 | 2009-01-14 | 2009-10-02 | TM-CHARGE-CODE | P3 ME | xxxxx | xxxxx | 99008 | 0 | 0 | 99008 | Main | UK | COMPLETE | a |  | #N/A | #N/A | #N/A | #N/A | #N/A | [10 empty] | 37.11% | [21 empty] | 97552 | 61349.95 | 1456 | 97552 | 61349.95 | 1456 | #N/A
19604 |  | Project 19 | 18659 | 2009-03-19 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 15671.7 | 0 | 0 | 15671.7 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [5 empty] | 50.38% | [5 empty] | 50.33% | [15 empty] | 10743.2 | 5331.03 | 4928.5 | 12179.79 | 5936.09 | 3491.91 | #N/A
19622 |  | Project 20 | 18786 | 2009-03-13 | 2009-09-04 | TM | P3 ME | xxxxx | xxxxx | 24333.2 | 0 | 0 | 24333.2 | Data Management | US | COMPLETE | a |  | #N/A | #N/A | #N/A | #N/A | #N/A | [10 empty] | 44.07% | [5 empty] | 45.13% | [15 empty] | 15866.65 | 8874.78 | 8466.55 | 15866.65 | 8874.78 | 8466.55 | #N/A
19642 | EL 374380 | Project 21 | 18870 | 2009-03-13 | 2009-12-07 | TM | P3 ME | xxxxx | xxxxx | 100447.28 | 0 | 0 | 100447.28 | Data Management | US | COMPLETE | a |  | #N/A | #N/A | #N/A | #N/A | #N/A | [7 empty] | n | n |  | 51.49% | [5 empty] | 51.8% | [15 empty] | 90421.7 | 43860.32 | 10025.58 | 100492.51 | 48728.98 | -45.23 | #N/A
19708 | EL 375077 | Project 22 | 18933 | 2009-04-02 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 430883.36 | 0 | 0 | 430883.36 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n |  |  | n | n | a | 53.66% | [5 empty] | 38.37% | a | n | [13 empty] | 347061.62 | 160824.26 | 83821.74 | 443577.87 | 193275.68 | -12694.51 | #N/A
19709 |  | Project 23 |  | 2008-05-01 | 2010-05-30 | TM | P3 ME | xxxxx | xxxxx | 327715.88 | 0 | 0 | 327715.88 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [5 empty] | 38.53% |  |  | a |  |  | -274.7% | a | n | [13 empty] | 74975.15 | 46085.58 | 252740.73 | 111416.42 | 66186.35 | 216299.46 | #N/A
19727 | EL 375087 | Project 24 |  | 2008-07-01 | 2009-10-31 | TM | P3 ME | xxxxx | xxxxx | 15241.05 | 0 | 9057 | 24298.05 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | 2010-01-25 | 9057 |  |  | n |  |  | n |  | a | 32.86% |  |  | a |  |  | -672.8% |  | n | [11 empty] | Fully Executed | 2010-01-25 | 13305.32 | 8932.88 | 1935.73 | 17310.32 | 11315.71 | -2069.27 | #N/A
19757 | EL 382102 | Project 25 | 17765 | 2008-09-23 | 2009-12-25 | FP | P3 ME | xxxxx | xxxxx | 510000 | 0 | 0 | 510000 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | a |  |  |  |  | 28.52% |  |  | a |  |  | -199.1% | a | n | [19 empty] | #N/A
19824 | EL 381703 | Project 26 |  | 2008-10-20 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 14921.9 | 0 | 0 | 14921.9 | Data Management | US | COMPLETE | a |  | #N/A | #N/A | #N/A | #N/A | #N/A | [10 empty] | 47% |  |  | a |  |  | -147.4% |  | n | [13 empty] | 14403.73 | 7634.19 | 518.17 | 14403.73 | 7634.19 | 518.17 | #N/A
19825 | EL 383912 | Project 27 | 18252 | 2009-01-01 | 2010-01-15 | FP | P3 ME | xxxxx | xxxxx | 488000 | 0 | 0 | 488000 | 0 | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [5 empty] | 37.06% | [5 empty] | -5.171% |  | n | [19 empty] | #N/A
19852 | EL 384012 | Project 28 |  | 2009-03-02 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 59058 | 0 | 8808 | 67866 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | 2009-12-31 | 8808 |  |  | n |  |  | n |  | a | 47.62% |  |  | a |  |  | -653.9% |  | n | [11 empty] | Fully Executed | 2009-12-31 | 64591.18 | 33834.11 | -5533.18 | 63465.74 | 33087.32 | -4407.74 | #N/A
19901 | 399808 | Project 29 |  | 2008-10-01 | 2010-02-12 | TM-CHARGE-CODE | P3 ME | xxxxx | xxxxx | 186505 | 47320 | 0 | 233825 | Main | UK | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [5 empty] | 48.54% | [6 empty] | a | [11 empty] | no actuals yet |  |  | 127900.5 | 65813 | 105924.5 | 176676.5 | 90000 | 57148.5 | #N/A
19916 | EL 386600 | Project 30 | 18945 | 2009-01-01 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 10179.4 | 0 | 0 | 10179.4 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n |  |  |  |  | a | 46.96% | [5 empty] | 100% |  | n | [13 empty] | 10035.52 | 5322.51 | 143.88 | 10104.96 | 5355.39 | 74.44 | #N/A
19947 | EL 390300 | Project 31 |  | 2007-10-01 | 2009-10-31 | TM | P3 ME | xxxxx | xxxxx | 5178 | 0 | 0 | 5178 | Data Management | US | COMPLETE |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | [13 empty] | a |  |  | -24.21% | [15 empty] | 0 | 58.3 | 5178 | 0 | 58.3 | 5178 | #N/A
19978 |  | Project 32 | 15836 | 2008-06-01 | 2010-02-11 | TM | P3 ME | xxxxx | xxxxx | 0 | 47905 | 11095 | 59000 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | 2010-01-31 | 11095 |  |  | n | [5 empty] | 42.33% | [6 empty] | a | [12 empty] | Fully Executed | 2010-01-31 | 10773.37 | 6212.48 | 37131.63 | 17774.5 | 10256.03 | 30130.5 | #N/A
19993 | EL 390874 | Project 33 | 17510 | 2008-08-12 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 32811.05 | 0 | 0 | 32811.05 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [5 empty] | 71.14% | [5 empty] | 59.33% |  | n | [11 empty] | Negated | 2009-12-18 | 3271.17 | 943.91 | 29539.88 | 3844.49 | 5069.15 | 28966.56 | #N/A
19994 | EL 391516 | Project 34 |  | 2008-08-11 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 55709.66 | 0 | 0 | 55709.66 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [5 empty] | 54.59% |  |  | a | [18 empty] | 21766.25 | 9882.99 | 33943.41 | 28383.19 | 12875.31 | 27326.47 | #N/A
20009 | EL 397784 | Project 35 | 17594 | 2008-08-27 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 21773.52 | 0 | 0 | 21773.52 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [5 empty] | 52.47% | [5 empty] | 43.49% | a | n | [11 empty] | Negated | 2009-12-21 | 7716.54 | 3667.68 | 14056.98 | 9177.94 | 4459.94 | 12595.58 | #N/A
20041 | EL 404317 | Project 36 | 17729 | 2008-09-29 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 62240 | 0 | 0 | 62240 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [5 empty] | 55.15% | [5 empty] | 51.16% | [15 empty] | 8888.28 | 3986.5 | 53351.72 | 13248.54 | 5469.84 | 48991.46 | #N/A
20042 | EL 401120 | Project 37 |  | 2009-03-01 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 85601.12 | 0 | 0 | 85601.12 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [5 empty] | 56.49% | [5 empty] | -2058% |  | n | [13 empty] | 1797.79 | 782.15 | 83803.33 | 9770.58 | 4564.38 | 75830.54 | #N/A
20179 |  | Project 38 |  | 2009-04-01 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 15228.52 | 0 | 0 | 15228.52 | Data Management | US | COMPLETE |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | [10 empty] | 64.07% | [18 empty] | no actuals yet in period 3 |  |  | 2567.13 | 922.45 | 12661.39 | 9288.57 | 4711.8 | 5939.95 | #N/A
20181 | EL 403727 | Project 39 | 19027 | 2009-03-15 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 53788.68 | 0 | 0 | 53788.68 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [5 empty] | 41.72% | [21 empty] | 4152.1 | 2419.96 | 49636.58 | 44625.59 | 24279.57 | 9163.09 | #N/A
20195 |  | Project 40 | 18677 | 2009-02-02 | 2010-02-11 | TM | P3 ME | xxxxx | xxxxx | 0 | 48996 | 0 | 48996 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  |  | n | [11 empty] | 52.79% | [13 empty] | Negated | 2010-01-31 | 0 | 0 | 48996 | 2981.03 | 1807.84 | 46014.97 | #N/A
20392 |  | Project 41 | 0 | 2007-05-01 | 2010-01-15 | TM | P3 ME | xxxxx | xxxxx | 0 | 0 | 15000 | 15000 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | 2010-01-15 | 15000 |  |  | n | [11 empty] | 24.39% | [13 empty] | Fully Executed | 2010-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A
20396 |  | Project 42 | 15111 FEB2008 | 2009-01-01 | 2010-02-01 | TM | P3 ME | xxxxx | xxxxx | 0 | 0 | 39662 | 39662 | Data Management | US | OPEN |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | 2010-02-01 | 39662 |  |  | n | [11 empty] | 10.52% | [13 empty] | Fully Executed | 2010-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A
18263 |  | Project 43 | 15111 FEB2008 | 2009-01-01 | 2009-12-31 | TM-CHARGE-CODE | P3 ME | xxxxx | xxxxx | 130820 | 0 |  |  | Co 3 Projects | UK | OPEN | [17 empty] | 32.65% | [5 empty] | 33.67% | [11 empty] | Just added Talisman so don't have IFS figures yet | [9 empty] | 0 | -7504.39 | 72531.41
18264 |  | Project 44 | 0 | 2009-01-01 | 2009-12-31 | TM | P3 ME | xxxxx | xxxxx | 387140 | 0 |  |  | Co 3 Projects | UK | OPEN | [17 empty] | 24.66% |  |  |  |  | n | 30.5% | [11 empty] | Just added Talisman so don't have IFS figures yet | [9 empty] | 0 | -31386.76 | 303632.62
18635 |  | Project 45 | 15111 FEB2008 | 2009-01-01 | 2009-12-31 | TM-CHARGE-CODE | P3 ME | xxxxx | xxxxx | 20940 | 0 |  |  | Co 3 Projects | UK | OPEN | [17 empty] | 10.84% | [5 empty] | 13.62% | [11 empty] | Just added Talisman so don't have IFS figures yet | [9 empty] | 0 | 520.97 | 2886.1
18722 |  | Project 46 | 15111 FEB2008 | 2009-02-26 | 2009-05-05 | TM | P3 ME | xxxxx | xxxxx | 14760 | 0 |  |  | Co 3 Projects | UK | OPEN | [12 empty] | a |  |  |  |  | 33.9% | [5 empty] | 34.04% | [11 empty] | Just added Talisman so don't have IFS figures yet | [9 empty] | 0 | -5719.5 | 5350.5
18723 |  | Project 47 | 15111 FEB2008 | 2009-02-26 | 2009-05-05 | TM | P3 ME | xxxxx | xxxxx | 2890 | 0 |  |  | Co 3 Projects | UK | OPEN | [12 empty] | a | [10 empty] | 33.58% | [11 empty] | Just added Talisman so don't have IFS figures yet | [9 empty] | 0 | 0.25 | 2890
18755 |  | Project 48 | 15111 FEB2008 | 2009-04-01 | 2009-04-30 | TM | P3 ME | xxxxx | xxxxx | 8920 | 0 |  |  | Co 3 Projects | UK | OPEN | [12 empty] | a | [10 empty] | 30.71% | a | [20 empty] | #N/A | -0.51 | 8920
18906 |  | Project 49 | 15111 FEB2008 | 2009-04-01 | 2009-06-30 | TM-CHARGE-CODE | P3 ME | xxxxx | xxxxx | 20940 | 0 |  |  | Co 3 Projects | UK | OPEN | [12 empty] | a |  |  |  |  | 12.4% | [5 empty] | 12.4% | a | [20 empty] | #N/A | -4535.25 | 16403.26
18224 |  | Project 50 |  | 2009-01-01 | 2009-12-31 | FUP | P3 ME | xxxxx | xxxxx | 186811 | 0 |  |  | Co 2 | UK | OPEN | [20 empty] | a |  |  |  | a | [10 empty] | Just added | [9 empty] | #N/A | 186811 | 186811
18101 |  | Project 51 |  | 2009-01-01 | 2009-12-31 | UNKNOWN | P3 ME | xxxxx | xxxxx | 0 | 0 |  |  | Up | UK | OPEN | [14 empty] | n | n |  | -1828% |  |  | a |  | n | -4871% |  | n | [10 empty] | Over run = -12.44K. | [8 empty] | #N/A | -12902.51 | -12437.41
18102 |  | Project 52 |  | 2009-01-01 | 2009-12-31 | UNKNOWN | P3 ME | xxxxx | xxxxx | 0 | 0 |  |  | Up | UK | OPEN | [14 empty] | n | n |  | -6478% |  |  | a |  |  | -16618% |  | n | [10 empty] | Over run = -3.66K. | [8 empty] | #N/A | -3659.09 | -3659.09