## Project List
[17 empty] | 53 | 53 | 53
[17 empty] | 7014912.81 | 11809334.48 | 4794421.67
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76
Project # | Project Name | Rate Card | Start POP | End POP | Project Type | Period | Project Manager | Project Controller | Burn Rate (rev) | Actual Cost | ETC | EAC Cost | Unbillable Cost | RO Cost | Cost Variance | Project Mark-up Rate | EAC Revenue | RO Revenue | Revenue Delta | Revenue Delta Sort Column | EAC Gross Margin | GM % | Markup Rate | RO Hours | EAC Hours | Hour Variance | Project Complete | Profit Center | Contract | Cost Variance in relation to Last Period | Prior EAC Revenue | Revenue Variance in relation to last period | Prior GM | Prior GM% | Prior Markup Rate | GM % Variance | GM % Mark-up Rate | Write Up/ Write Down | Calc PTD Invoice Value | Billing Invoice Value | Variance | IFS PTD Invoice Value | PTD Tax | PTD Inv. Amount w/tax | Burn Rate (cost) | RO Value Rank | EAC Value Rank | Project # (Value) | Project # (Text) | Project Manager Comments | Status | SPA | Value | Exp | Status | BCA | BCA $ | BCA cost | IFS SPA check | EAC Date | POP ext | SPA cost | IWOs | IWO $ | IWO start | IWO end | WBS closed | Elance Prj | BP BU | Labor Discount | UK interco | Q1 exch (billing) | Q2 exch (billing) | Q3 exch (billing) | Q4 exch (billing)
16267 | xxxxxx | xxx | 2008-12-08 | 2009-02-27 | TM | P2 ME | xxxxxxx | xxxxxxx | 0% | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 313376 | 313376 | 313376 | 0 | #DIV/0! | #DIV/0! | 0 |  |  | OPEN | 8903 | xxxxxx | GBP | [8 empty] | 0 |  |  | 0 |  |  |  |  | 45 | 16267 | 16267 | 16267.01.067.PETRO.003, 16267.01.067.PETRO.004 |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed
16520 | xxxxxx | 16520 | 2008-01-31 | 2009-03-21 | TM | P3 ME | xxxxxxx | xxxxxxx | 71.37% | 68627.97 | 0 | 68627.97 |  | 98363 | 29735.03 |  | 148777.06 | 208458 | 59680.94 | 59680.94 | 80149.09 | 53.87% | 116.8% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 148777.06 | 148300.74 | 476.32 | 148777.06 |  |  | 69.77% |  | 10 | 16520 | 16520 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed | EL 213697
17130 | xxxxxx | 17130 | 2008-05-12 | 2009-06-01 | TM | P3 ME | xxxxxxx | xxxxxxx | 71.35% | 186436.24 | 27979.52 | 214415.76 |  | 272728 | 58312.24 |  | 311067.74 | 372329 | 61261.26 | 61261.26 | 96651.98 | 31.07% | 45.08% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 265660.1 | 243220.9 | 22439.2 | 265660.1 |  |  | 68.36% |  | 7 | 17130 | 17130 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
17517 | xxxxxx | 17517 | 2008-08-01 | 2009-03-15 | TM | P3 ME | xxxxxxx | xxxxxxx | 91.22% | 25750.73 | 0 | 25750.73 |  | 22969 | -2781.73 |  | 50972.7 | 55879 | 4906.3 | 4906.3 | 25221.97 | 49.48% | 97.95% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 50972.7 | 50972.66 | 0.04 | 50972.7 |  |  | 112.1% |  | 20 | 17517 | 17517 | Project complete per J Willimas 4-19/09 email |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed
17526 | xxxxxx | 17526 | 2008-08-08 | 2009-01-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 89.91% | 59189.4 | 0 | 59189.4 |  | 70326 | 11136.6 |  | 121353.25 | 134965 | 13611.75 | 13611.75 | 62163.85 | 51.23% | 105% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 121353.25 | 121353.1 | 0.15 | 121353.25 |  |  | 84.16% |  | 14 | 17526 | 17526 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed |  | NAG
17612 | xxxxxx | 17612 | 2008-09-01 | 2008-12-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 100% | 65906.65 | 0 | 65906.65 |  | 81592 | 15685.35 |  | 147048.96 | 147042 | -6.96 | 6.96 | 81142.31 | 55.18% | 123.1% | 0 |  |  | CLOSED | 2293 | xxxxxx | USD | [8 empty] | 147048.96 | 146518.15 | 530.81 | 147048.96 |  |  | 80.78% |  | 11 | 17612 | 17612 |  |  |  | 0 |  |  |  | 0 | 0 |  |  |  | 0 |  |  |  |  | Closed | EL 277691
17970 | xxxxxx | 17970 P13 TO DEC 31 | 2009-01-01 | 2009-06-26 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | 83.61% | 283038.86 | 97610.7 | 380649.56 |  | 303745 | -76904.56 |  | 648696.75 | 546197 | -102499.75 | 102499.75 | 268047.19 | 41.32% | 70.42% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 456677.47 |  |  | 456677.47 |  |  | 93.18% |  | 3 | 17970 | 17970 | Original: BCA for $152,436.11 (10/20/2008 - 12/31/2008) not covered by Elance order |  | 30956 | 0 | 2009-04-20 | Cancelled | yes | 0 | 0 |  |  |  | 0 | [6 empty] | DCT
17972 | xxxxxx | 17972 | 2008-10-20 | 2008-12-31 | TM | P3 ME | xxxxxxx | xxxxxxx | #DIV/0! | 4389.51 | 0 | 4389.51 |  | 0 | -4389.51 |  | 10278.78 | 0 | -10278.78 | 10278.78 | 5889.27 | 57.3% | 134.2% | 0 |  |  | CLOSED | 2293 | xxxxxx | USD | [8 empty] | 10278.78 |  |  | 10278.78 |  |  |  |  | 35 | 17972 | 17972 |  |  |  | 0 |  |  | yes | 37178 | 16686 |  |  |  | 0 |  |  |  |  | Closed
18008 | xxxxxx | 18008 P2FY10 MAR 1 | 2008-11-24 | 2009-04-03 | TM | P3 ME | xxxxxxx | xxxxxxx | 107.2% | 54245.47 | 0 | 54245.47 |  | 68112 | 13866.53 |  | 113066.41 | 105457 | -7609.41 | 7609.41 | 58820.94 | 52.02% | 108.4% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 113066.41 | 63648.81 | 49417.6 | 113066.41 |  |  | 79.64% |  | 15 | 18008 | 18008 |  |  | 30819 | 0 | 2009-05-01 | Negated |  | 0 | 0 |  |  |  | 0 |  |  |  |  | Closed
18171 | xxxxxx | 18171 | 2009-01-02 | 2009-12-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 28.64% | 58401.29 | 137531.46 | 195932.75 |  | 208389 | 12456.25 |  | 427716.65 | 454355 | 26638.35 | 26638.35 | 231783.9 | 54.19% | 118.3% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 130148.85 |  |  | 130148.85 |  |  | 28.03% |  | 4 | 18171 | 18171 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18172 | xxxxxx | 18172 | 2009-01-02 | 2009-12-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 31.67% | 87281.75 | 122447.76 | 209729.51 |  | 181839 | -27890.51 |  | 377605.3 | 383349 | 5743.7 | 5743.7 | 167875.79 | 44.46% | 80.04% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 121398.27 |  |  | 121398.27 |  |  | 48% |  | 6 | 18172 | 18172 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18333 | xxxxxx | 18333 | 2009-01-05 | 2009-12-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 31.76% | 28022.37 | 61244.66 | 89267.03 |  | 103223 | 13955.97 |  | 163652.02 | 166993 | 3340.98 | 3340.98 | 74384.99 | 45.45% | 83.33% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 53039.46 |  |  | 53039.46 |  |  | 27.15% |  | 9 | 18333 | 18333 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 | [5 empty] | EL 319601
18348 | xxxxxx | 18348 | 2008-12-01 | 2009-08-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 49.29% | 12548.71 | 11106.84 | 23655.55 |  | 27461 | 3805.45 |  | 62029.63 | 67018 | 4988.37 | 4988.37 | 38374.08 | 61.86% | 162.2% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 33029.88 | 22415.71 | 10614.17 | 33029.88 |  |  | 45.7% |  | 19 | 18348 | 18348 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 | [5 empty] | EL 319535
18942 | xxxxxx | 18942 | 2009-03-30 | 2009-05-20 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | #DIV/0! | 587.4 | 6306.56 | 6893.96 |  | 0 | -6893.96 |  | 15522.57 | 0 | -15522.57 | 15522.57 | 8628.61 | 55.59% | 125.2% | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 1328.15 |  |  | 1328.15 |  |  |  |  | 31 | 18942 | 18942 |  |  |  | 0 |  |  |  | 15523 | 7135 |  |  |  | 0 | [6 empty] | NAG
19155 | xxxxxx | 19155 | 2009-04-27 | 2009-12-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 0% | 0 | 0 | 0 |  | 39918.74 | 39918.74 |  | 0 | 69852.54 | 69852.54 | 69852.54 | 0 | #DIV/0! | #DIV/0! | 0 |  |  | OPEN | 2293 | xxxxxx | USD | [8 empty] | 0 |  |  | 0 |  |  | 0% |  | 45 | 19155 | 19155 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
17648 | xxxxxx | 17648 | 2008-09-01 | 2009-02-27 | TM | P3 ME | xxxxxxx | xxxxxxx | 68.77% | 22534.41 | 0 | 22534.41 |  | 39165 | 16630.59 |  | 44978.99 | 65405 | 20426.01 | 20426.01 | 22444.58 | 49.9% | 99.6% | 0 |  |  | OPEN | 8901 | xxxxxx | GBP | [8 empty] | 44978.99 | 52158.34 | -7179.35 | 44978.99 |  |  | 57.54% |  | 23 | 17648 | 17648 | supposed to be complete |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed |  | GOM
17649 | xxxxxx | 17649 | 2008-09-04 | 2008-12-03 | TM | P3 ME | xxxxxxx | xxxxxxx | 20.43% | 801.43 | 0 | 801.43 |  | 6228 | 5426.57 |  | 2124.95 | 10400 | 8275.05 | 8275.05 | 1323.52 | 62.28% | 165.1% | 0 |  |  | CLOSED | 8901 | xxxxxx | 0 | [8 empty] | 2124.95 | 2496.29 | -371.34 | 2124.95 |  |  | 12.87% |  | 43 | 17649 | 17649 | supposed to be complete |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed |  | EPTG
18367 | xxxxxx | 18367 | 2009-01-14 | 2009-12-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 0% | 0 | 0 | 0 |  | 3476.62 | 3476.62 |  | 0 | 9000 | 9000 | 9000 | 0 | #DIV/0! | #DIV/0! | 0 |  |  | OPEN | 8901 | xxxxxx | GBP | [8 empty] | 0 |  |  | 0 |  |  | 0% |  | 45 | 18367 | 18367 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 | [6 empty] | NAG
18659 | xxxxxx | 18659 | 2009-03-19 | 2009-06-29 | TM | P3 ME | xxxxxxx | xxxxxxx | 69.3% | 17539.62 | 7297.95 | 24837.57 |  | 26748 | 1910.43 |  | 50000.5 | 49913 | -87.5 | 87.5 | 25162.93 | 50.33% | 101.3% | 0 |  |  | OPEN | 8901 | xxxxxx | GBP | [8 empty] | 34589.08 |  |  | 34589.08 |  |  | 65.57% |  | 21 | 18659 | 18659 |  | US IWO 18660 |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 | 18660 | 150192.5 | 2009-02-16 | 2009-11-30 |  |  | NAG
18786 | xxxxxx | 18786 | 2009-03-13 | 2009-12-27 | TM | P3 ME | xxxxxxx | xxxxxxx | 11.93% | 9845.02 | 59150.65 | 68995.67 |  | 66824 | -2171.67 |  | 125739.83 | 125000 | -739.83 | 739.83 | 56744.16 | 45.13% | 82.24% | 0 |  |  | OPEN | 8901 | xxxxxx | GBP | [8 empty] | 14912.75 |  |  | 14912.75 |  |  | 14.73% |  | 13 | 18786 | 18786 |  | US IWO 18804 |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 | 18804 | 1382 | 2009-01-09 | 2009-04-30
18870 | xxxxxx | 18870 | 2009-03-13 | 2009-05-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 20.96% | 2943.98 | 7839 | 10782.98 |  | 17964 | 7181.02 |  | 22370.12 | 30000 | 7629.88 | 7629.88 | 11587.14 | 51.8% | 107.5% | 0 |  |  | OPEN | 8901 | xxxxxx | GBP | [8 empty] | 6289.37 |  |  | 6289.37 |  |  | 16.39% |  | 26 | 18870 | 18870 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 | [6 empty] | DCT
18933 | xxxxxx | 18933 | 2009-04-02 | 2009-04-30 | TM | P3 ME | xxxxxxx | xxxxxxx | 0% | 0 | 1373.1 | 1373.1 |  | 0 | -1373.1 |  | 2228.1 | 2230 | 1.9 | 1.9 | 855 | 38.37% | 62.27% | 0 |  |  | OPEN | 8901 | xxxxxx | GBP | [8 empty] | 0 |  |  | 0 |  |  |  |  | 42 | 18933 | 18933 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed |  | Other
17108 | xxxxxx |  | 2008-05-01 | 2009-05-12 | FP | P3 ME | xxxxxxx | xxxxxxx | 0% | 132878.25 | 14240.2 | 147118.45 |  | 118228 | -28890.45 |  | 39258.67 | 197440 | 158181.33 | 158181.33 | -107859.78 | -274.7% | -73.31% | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 0 | 159567.38 | -159567.38 | 39258.67 |  |  | 112.4% |  | 24 | 17108 | 17108 | SA France (2031) |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 | [6 empty] | GOM
17295 | xxxxxx |  | 2008-07-01 | 2008-12-31 | FFP | P3 ME | xxxxxxx | xxxxxxx | 0% | 38497.68 | 0 | 38497.68 |  | 29914 | -8583.68 |  | 4981.86 | 40087 | 35105.14 | 35105.14 | -33515.82 | -672.8% | -87.06% | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 0 | 46100.91 | -46100.91 | 4981.86 |  |  | 128.7% |  | 39 | 17295 | 17295 | Project work (1959); might be complete |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed |  | NAGP
17765 | xxxxxx | 17765 | 2008-09-23 | 2009-12-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 18.64% | 71188.75 | 0 | 71188.75 |  | 342154 | 270965.25 |  | 111497.92 | 598232 | 486734.08 | 486734.08 | 40309.17 | 36.15% | 56.62% | 0 |  |  | OPEN | 2232 | xxxxxx | USD | [8 empty] | 111497.92 |  |  | 111497.92 |  |  | 20.81% |  | 16 | 17765 | 17765 | Was renegotiated. New project number is 18945 |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 | [6 empty] | DCT
17856 | xxxxxx |  | 2008-10-20 | 2008-12-20 | FFP | P3 ME | xxxxxxx | xxxxxxx | 0% | 48513.26 | 0 | 48513.26 |  | 0 | -48513.26 |  | 19607.27 | 64776 | 45168.73 | 45168.73 | -28905.99 | -147.4% | -59.58% | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 0 | 64776 | -64776 | 19607.27 |  |  |  |  | 29 | 17856 | 17856 | SA France (2031) | US IWO 17949 |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 | 17949 |  |  |  | Closed
18252 | xxxxxx | 18252 | 2009-01-01 | 2009-12-31 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | #DIV/0! | 55586.67 | 138551.52 | 194138.19 |  | 0 | -194138.19 |  | 206373.47 | 0 | -206373.47 | 206373.47 | 12235.28 | 5.929% | 6.302% | 0 |  |  | OPEN | 8904 | xxxxxx | 0 | [8 empty] | 59754.63 | 55968.55 | 3786.08 | 59754.63 |  |  |  |  | 8 | 18252 | 18252 | Need to change profit center to 8909 (1880 - Subsurface Data Management Info); has management fee; check on that credit |  |  | 0 |  |  |  | 0 | 0 |  |  |  | 0
18361 | xxxxxx |  | 2009-03-02 | 2009-04-30 | FFP | P3 ME | xxxxxxx | xxxxxxx | 0% | 35344.34 | 6210.39 | 41554.73 |  | 38449 | -3105.73 |  | 5511.8 | 54320 | 48808.2 | 48808.2 | -36042.93 | -653.9% | -86.74% | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 0 | 54320 | -54320 | 0 |  |  | 91.93% |  | 38 | 18361 | 18361 | Total SA |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 | [6 empty] | EPTG
18733 | xxxxxx |  | 2008-10-01 | 2009-03-31 | FP | P3 ME | xxxxxxx | xxxxxxx | 0% | 0 | 0 | 0 |  | 1497 | 1497 |  | 0 | 2500 | 2500 | 2500 | 0 | #DIV/0! | #DIV/0! | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 0 |  |  | 0 |  |  | 0% |  | 45 | 18733 | 18733 | Project work (1959) |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18945 | xxxxxx | 18945 | 2009-01-01 | 2010-12-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 0% | 0 | 0 | 0 |  | 582403 | 582403 |  | 854627.36 | 839727 | -14900.36 | 14900.36 | 854627.36 | 100% | #DIV/0! | 0 |  |  | OPEN | 2232 | xxxxxx | USD | [8 empty] | 0 |  |  | 106027.36 |  |  | 0% |  | 2 | 18945 | 18945 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
15773 | xxxxxx |  | 2007-10-01 | 2010-09-30 | FP | P3 ME | xxxxxxx | xxxxxxx | 0% | 109001.42 | 0 | 109001.42 |  | 82921.7 | -26079.72 |  | 87758.66 | 290225.94 | 202467.28 | 202467.28 | -21242.76 | -24.21% | -19.49% | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 0 | 0 | 0 | 87758.66 |  |  | 131.5% |  | 17 | 15773 | 15773 | Documentum support (1667); MSA (2075) |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
15836 | xxxxxx | 15836 | 2008-06-01 | 2008-07-15 | TM | P3 ME | xxxxxxx | xxxxxxx | 0% | 0 | 0 | 0 |  | 4493 | 4493 |  | 0 | 7504 | 7504 | 7504 | 0 | #DIV/0! | #DIV/0! | 0 |  |  | COMPLETE | 8909 | xxxxxx | GBP | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0% |  | 45 | 15836 | 15836 | Project work (1959) |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed
17510 | xxxxxx | 17510 | 2008-08-12 | 2008-12-19 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | 85% | 4321.43 | 0 | 4321.43 |  | 7486 | 3164.57 |  | 10625.73 | 12501 | 1875.27 | 1875.27 | 6304.3 | 59.33% | 145.9% | 0 |  |  | CLOSED | 8909 | xxxxxx | GBP | [8 empty] | 10625.73 | 0 | 10625.73 | 10625.73 |  |  | 57.73% |  | 34 | 17510 | 17510 | Documentum support (1667) |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed
17576 | xxxxxx |  | 2008-08-11 | 2008-12-31 | FP | P3 ME | xxxxxxx | xxxxxxx | 0% | 6628.45 | 0 | 6628.45 |  | 3744 | -2884.45 |  | 0 | 6252 | 6252 | 6252 | -6628.45 | #DIV/0! | -100% | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 0 | 0 | 0 | 0 |  |  | 177% |  | 45 | 17576 | 17576 | Documentum support (1667) |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
17594 | xxxxxx | 17594 | 2008-08-27 | 2009-03-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 67.21% | 7497.08 | 0 | 7497.08 |  | 11821 | 4323.92 |  | 13267.14 | 19741 | 6473.86 | 6473.86 | 5770.06 | 43.49% | 76.96% | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 13267.14 | 0 | 13267.14 | 13267.14 |  |  | 63.42% |  | 32 | 17594 | 17594 | Documentum support (1667) |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed
17729 | xxxxxx | 17729 | 2008-09-29 | 2009-03-31 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | 97.47% | 23808.09 | 0 | 23808.09 |  | 29951 | 6142.91 |  | 48751.14 | 50018 | 1266.86 | 1266.86 | 24943.05 | 51.16% | 104.8% | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 48751.14 | 0 | 48751.14 | 48751.14 |  |  | 79.49% |  | 22 | 17729 | 17729 | Documentum support (1667) |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed
18901 | xxxxxx |  | 2009-03-01 | 2010-02-28 | FP | P3 ME | xxxxxxx | xxxxxxx | #DIV/0! | 2089.9 | 43015.43 | 45105.33 |  | 0 | -45105.33 |  | 2089.9 | 0 | -2089.9 | 2089.9 | -43015.43 | -2058% | -95.37% | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 0 |  |  | 2089.9 |  |  |  |  | 44 | 18901 | 18901 |  |  |  | 0 |  |  |  | 81961.93 | 53275.25 |  |  |  | 0
18988 | xxxxxx |  | 2009-04-01 | 2010-03-31 | FP | P3 ME | xxxxxxx | xxxxxxx | 0% | 0 | 0 | 0 |  | 1617 | 1617 |  | 0 | 2700 | 2700 | 2700 | 0 | #DIV/0! | #DIV/0! | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 0 |  |  | 0 |  |  | 0% |  | 45 | 18988 | 18988 | Total UK - MSA (2075) |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
19027 | xxxxxx | 19027 | 2009-03-15 | 2009-04-30 | TM | P3 ME | xxxxxxx | xxxxxxx | 0% | 0 | 0 | 0 |  | 3492 | 3492 |  | 0 | 5831 | 5831 | 5831 | 0 | #DIV/0! | #DIV/0! | 0 |  |  | OPEN | 8909 | xxxxxx | GBP | [8 empty] | 0 |  |  | 0 |  |  | 0% |  | 45 | 19027 | 19027 | Total UK - MSA (2075) |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18677 | xxxxxx | 18677 | 2009-02-02 | 2009-06-26 | TM | P3 ME | xxxxxxx | xxxxxxx | 92.95% | 18672.4 | 11462.23 | 30134.63 |  | 25460 | -4674.63 |  | 63837.72 | 41500 | -22337.72 | 22337.72 | 33703.09 | 52.79% | 111.8% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 38572.72 | 38916.39 | -343.67 | 38572.72 |  |  | 73.34% |  | 18 | 18677 | 18677 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
15111 | xxxxxx | 0 | 2007-05-01 | 2008-12-21 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | 32.61% | 1356192.84 | 174456.36 | 1530649.2 |  | 4435797 | 2905147.8 |  | 2024279.64 | 5456030 | 3431750.36 | 3431750.36 | 493630.44 | 24.39% | 32.25% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 1778989.8 | 0 | 1778989.8 | 1778989.8 |  |  | 30.57% |  | 1 | 15111 | 15111 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0 |  |  |  |  | Closed
18261 | xxxxxx | 15111 FEB2008 | 2009-01-01 | 2009-12-31 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | 0.9497% | 175.94 | 15355.43 | 15531.37 |  | 0 | -15531.37 |  | 17357.65 | 22330 | 4972.35 | 4972.35 | 1826.28 | 10.52% | 11.76% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 212.06 | 0 | 212.06 | 212.06 |  |  |  |  | 30 | 18261 | 18261 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18262 | xxxxxx | 0 | 2009-01-01 | 2009-12-31 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | 45.04% | 2323.27 | 3479.55 | 5802.82 |  | 0 | -5802.82 |  | 8259.78 | 7180 | -1079.78 | 1079.78 | 2456.96 | 29.75% | 42.34% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 3233.92 | 0 | 3233.92 | 3233.92 |  |  |  |  | 37 | 18262 | 18262 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18263 | xxxxxx | 15111 FEB2008 | 2009-01-01 | 2009-12-31 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | 44.56% | 39257.9 | 52494.38 | 91752.28 |  | 0 | -91752.28 |  | 138324.39 | 130820 | -7504.39 | 7504.39 | 46572.11 | 33.67% | 50.76% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 58288.59 | 0 | 58288.59 | 58288.59 |  |  |  |  | 12 | 18263 | 18263 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18264 | xxxxxx | 0 | 2009-01-01 | 2009-12-31 | TM | P3 ME | xxxxxxx | xxxxxxx | 21.57% | 62915.37 | 227955.96 | 290871.33 |  | 0 | -290871.33 |  | 418526.76 | 387140 | -31386.76 | 31386.76 | 127655.43 | 30.5% | 43.89% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 83507.38 | 0 | 83507.38 | 83507.38 |  |  |  |  | 5 | 18264 | 18264 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18635 | xxxxxx | 15111 FEB2008 | 2009-01-01 | 2009-12-31 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | 86.22% | 16096.36 | 1542 | 17638.36 |  | 0 | -17638.36 |  | 20419.03 | 20940 | 520.97 | 520.97 | 2780.67 | 13.62% | 15.76% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 18053.9 | 0 | 18053.9 | 18053.9 |  |  |  |  | 28 | 18635 | 18635 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18722 | xxxxxx | 15111 FEB2008 | 2009-02-26 | 2009-05-05 | TM | P3 ME | xxxxxxx | xxxxxxx | 63.75% | 6220.04 | 7287.75 | 13507.79 |  | 0 | -13507.79 |  | 20479.5 | 14760 | -5719.5 | 5719.5 | 6971.71 | 34.04% | 51.61% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 9409.5 |  |  | 9409.5 |  |  |  |  | 27 | 18722 | 18722 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18723 | xxxxxx | 15111 FEB2008 | 2009-02-26 | 2009-05-05 | TM | P3 ME | xxxxxxx | xxxxxxx | 0% | -0.55 | 1920 | 1919.45 |  | 0 | -1919.45 |  | 2889.75 | 2890 | 0.25 | 0.25 | 970.3 | 33.58% | 50.55% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 0 |  |  | 0 |  |  |  |  | 41 | 18723 | 18723 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18755 | xxxxxx | 15111 FEB2008 | 2009-04-01 | 2009-04-30 | TM | P3 ME | xxxxxxx | xxxxxxx | 0% | -0.18 | 6181.51 | 6181.33 |  | 0 | -6181.33 |  | 8920.51 | 8920 | -0.51 | 0.51 | 2739.18 | 30.71% | 44.31% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 0 |  |  | 0 |  |  |  |  | 36 | 18755 | 18755 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18906 | xxxxxx | 15111 FEB2008 | 2009-04-01 | 2009-06-30 | TM-CHARGE-CODE | P3 ME | xxxxxxx | xxxxxxx | 21.67% | 3974.1 | 18342 | 22316.1 |  | 12539 | -9777.1 |  | 25475.25 | 20940 | -4535.25 | 4535.25 | 3159.15 | 12.4% | 14.16% | 0 |  |  | OPEN | 8904 | xxxxxx | GBP | [8 empty] | 4536.74 |  |  | 4536.74 |  |  | 31.69% |  | 25 | 18906 | 18906 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18224 | xxxxxx |  | 2009-01-01 | 2009-12-31 | FUP | P3 ME | xxxxxxx | xxxxxxx | 0% | 21993.83 | 119774.31 | 141768.14 |  | 0 | -141768.14 |  | 0 | 186811 | 186811 | 186811 | -141768.14 | #DIV/0! | -100% | 0 |  |  | OPEN | 8903 | xxxxxx | GBP | [8 empty] | 0 |  |  | 0 |  |  |  |  | 45 | 18224 | 18224 |  |  |  | 0 |  |  |  | 0 | 0 |  |  | x | 0
18101 | xxxxxx |  | 2009-01-01 | 2009-12-31 | UNKNOWN | P3 ME | xxxxxxx | xxxxxxx | #DIV/0! | 239768.14 | 401660.73 | 641428.87 |  | 0 | -641428.87 |  | 12902.51 | 0 | -12902.51 | 12902.51 | -628526.36 | -4871% | -97.99% | 0 |  |  | OPEN | 8903 | xxxxxx | GBP | [8 empty] | 12437.41 |  |  | 12902.51 |  |  |  |  | 33 | 18101 | 18101 | Intercompany 18214 |  |  | 0 |  |  |  | 0 | 0 |  |  |  | 0
18102 | xxxxxx |  | 2009-01-01 | 2009-12-31 | UNKNOWN | P3 ME | xxxxxxx | xxxxxxx | #DIV/0! | 240678.08 | 371066.04 | 611744.12 |  | 0 | -611744.12 |  | 3659.09 | 0 | -3659.09 | 3659.09 | -608085.03 | -16618% | -99.4% | 0 |  |  | OPEN | 8903 | xxxxxx | GBP | [8 empty] | 3659.09 |  |  | 3659.09 |  |  |  |  | 40 | 18102 | 18102 | Intercompany 18215 |  |  | 0 |  |  |  | 0 | 0 |  |  |  | 0